## Inspection
[14 empty] | Mã số tài liệu |  | RV-SRS-NV-01
[14 empty] | Ngày |  | 2017-11-30
[5 empty] | Tên tài liệu: |  |  | [K14][FINAL]Review_ThietKeChucNangHeThong | [5 empty] | Tên công ty |  | Bitech
[14 empty] | Bộ phận review |  | Software
[5 empty] | Tên dự án: |  |  | Quản lý Tour
[16 empty] | Chấp nhận bởi |  | Tạo bởi
Thiên Hoàng
[5 empty] | Giai đoạn: |  |  | Phân tích
Mục tiêu review |  |  |  | Hoàn thành việc mô tả đúng với yêu cầu class đã post trên group
Các bên tham gia |  |  |  | Điều phối |  | Thiên Hoàng |  | Người tạo | Thiên Hoàng |  | Thư kí |  |  |  | Phiên bản tài liệu |  | Thống kê
|  |  |  | Người review |  |  | Thiên Hoàng | [7 empty] | RVC-1 |  |  |  | Line
On-desk check |  |  |  | Bắt đầu ngày |  | 2017-11-28 |  | Kết thúc ngày | 2017-11-30 |  | Sô lượng người review |  | 1
Meeting |  |  |  | Ngày họp |  |  |  | Thời gian bắt đầu |  |  | Thời gian kết thúc
Mã số file |  | Mô tả file | [6 empty] | File name | [9 empty] | (Select from list)
① |  | Review Thiết kế hệ thống[FINAL] _ Hà Đình Nhân | [6 empty] | DD2 1412367.docx | [5 empty] | Version1: https://github.com/NguyenThaiHoc1/QuanLyTour-BiTech/tree/master/Report/K14/1412367/So%20do%20lop%20chi%20tiet%20va%20he%20thong |  |  |  | Page
② |  | Review Thiết kế hệ thống [FINAL] _ Nguyễn Thái Học | [6 empty] | [DD]KhachHang-Ver3.docx | [5 empty] | Version1: https://github.com/NguyenThaiHoc1/QuanLyTour-BiTech/blob/master/Report/K14/1412193/%5BDD%5DKhachHang-Ver3.docx |  |  |  | Page
③ |  | Review Thiết kế hệ thống [FINAL] _ Trần Thiên Hoàng | [6 empty] | [DD] [FINAL] 1412185.docx | [5 empty] | Version1: https://github.com/NguyenThaiHoc1/QuanLyTour-BiTech/blob/master/Report/K14/1412185/%5BDD%5D%20%5BFINAL%5D%201412185.docx |  |  |  | Page
④ |  | Review Thiết kế hệ thống [FINAL] _ Bùi Đình Khánh | [6 empty] | [DD] [BiTech]DichVu/HoTroKhachHang.docx | [5 empty] | Version1: https://github.com/NguyenThaiHoc1/QuanLyTour-BiTech/tree/master/Report/K14/1412240 |  |  |  | (Select from list)
⑤ | [18 empty] | (Select from list)
No. | Vị trí phát hiện vấn đề |  | Phát hiện bởi | Mô tả |  |  |  |  | Phân loại |  | Xử lý bởi | Ngày hoàn thành |  | Mô tả giải pháp
| Mã số file | Vị trí
1 | ① | Sơ đồ lớp hệ thống/chi tiết | Thiên Hoàng | Chưa cập nhật hình ảnh mới của sơ đồ lớp hệ thống/chi tiết Ngay, TheThanhToan, NhanVien |  |  |  |  | Issue | Defect |  |  |  | Đã sửa
3 | ② | Sơ đồ lớp hệ thống/chi tiết | Thiên Hoàng | Chưa cập nhật hình ảnh mới của sơ đồ lớp hệ thống/chi tiết KhachHang |  |  |  |  | Issue | Risk |  |  |  | Đã sửa
4 | ④ | Thiếu Model | Thiên Hoàng | Chưa cập nhật Model DichVu, HoTroKhachHang |  |  |  |  | Issue | Other |  |  |  | Đã sửa
5 | (Select from list) | [7 empty] | Question | Problem
6 | (Select from list) | [7 empty] | Issue | Other
7 | (Select from list) | [7 empty] | Issue | Defect
8 | (Select from list) | [7 empty] | Issue | Risk
9 | (Select from list) | [7 empty] | Issue | Risk
10 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
11 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
12 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
13 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
14 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
15 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
16 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
17 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
18 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
19 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
20 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
21 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
22 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
23 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
24 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
25 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
26 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
27 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
28 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
29 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
30 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
31 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
32 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
33 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
34 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
35 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
36 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
37 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
38 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
39 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
40 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
41 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
42 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
43 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
44 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
45 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
46 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
47 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
48 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
49 | (Select from list) | [7 empty] | (Select from list) | (Select from list)
50 | (Select from list) | [7 empty] | (Select from list) | (Select from list)

## Walk-through
【RENESAS CONFIDENTIAL】 | [11 empty] | #REF!
Inform to: | [11 empty] | Document number
Date of issue
[5 empty] | Document name: | Peer review minutes | [5 empty] | Company name
Issuing department
Project name:
[14 empty] | Approved by |  |  | Created by
Project number:
Process name:
<Cell background color> Light blue: item name, yellow: data list, pink: automatically configured items, grey: invalid
Peer review checklist |  |  |  | (Select from list)
Objective of review (description of review)
Participants |  |  |  | Creator |  | Recorder |  |  | Reader |  |  |  | Review organizer
Reviewer
Meeting |  |  |  | Implementation date |  | Start time |  |  | End time |  |  |  | Meeting Number of participants |  |  | Meeting location
Review objects ※The work products indicated to be reviewed in "Project plan".
Object ID |  | Name |  |  |  |  | File name | [5 empty] | Version |  | Target scale
① | [17 empty] | (Select from list)
② | [17 empty] | (Select from list)
③ | [17 empty] | (Select from list)
④ | [17 empty] | (Select from list)
⑤ | [17 empty] | (Select from list)
⑥ | [17 empty] | (Select from list)
⑦ | [17 empty] | (Select from list)
⑧ | [17 empty] | (Select from list)
⑨ | [17 empty] | (Select from list)
⑩ | [17 empty] | (Select from list)
Total scale
List of Issue/Question/Resolution
No. | Location of issues |  | Detected by | Description of issue/question |  |  | Classification |  | Processed by | Completion date/Deadline |  | Description of resolution/Question answering |  |  |  |  | Verified by | Verification date
| Object ID | Location
1 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
2 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
3 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
4 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
5 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
6 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
7 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
8 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
9 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
10 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
11 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
12 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
13 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
14 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
15 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
16 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
17 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
18 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
19 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
20 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
21 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
22 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
23 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
24 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
25 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
26 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
27 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
28 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
29 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
30 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
31 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
32 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
33 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
34 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
35 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
36 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
37 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
38 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
39 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
40 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
41 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
42 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
43 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
44 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
45 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
46 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
47 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
48 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
49 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
50 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
Peer review evaluation
No. | Item |  |  |  |  | Description
1 | Review initiating condition |  |  |  |  | 【Review initiating conditions】 The initiating conditions of peer review are as follow: ①"7.3.Preparation of peer review" (Implementation Standard for Review) has completed. ②Required participants as specified in project plan are able to take part in. Describe below if the review initiating condition is other than ① and ②.
【Verification result of review initiating conditions】
2 | Review completing conditions |  |  |  |  | 【Review completing conditions】 The completing conditions of peer review are as follow: ①Desired values of analysis items of peer review, specified in project plan, have been obtained. Or, if desired values of analysis items have not been obtained, agreement with the reviewers regarding the reasons has been reached. ②Peer review minutes indicate that all actions regarding the detected issues have been completed. If unresolved issues exist, agreement with the reviewers regarding the reasons has been reached. Describe below if the completing condition is other than ① and ②.
【Verification results and evaluation regarding review completing conditions】
3 | Review measurements |  |  |  |  | 【Measured value】
[6 empty] | Meeting |  |  | Review duration |  |  |  | Number of participants |  |  | Review ｍan hour
Review scale (total)
[6 empty] | Number of review issues | 0 |  | Number of defects |  | 0
4 | Review analysis items and analysis evaluation |  |  |  |  | 【Analysis item】
[11 empty] | Target value |  | Performance value | Tailoring for analysis items
[6 empty] | Review defect density (number of review issues/review scale) | [7 empty] | (Select from list)
[6 empty] | Review speed (review scale/review duration) ※For meeting only | [7 empty] | (Select from list)
【Analysis evaluation】
5 | Review result evaluation according to initiating conditions, completing conditions, quality evaluation, and analysis evaluation |  |  |  |  | 【Review result evaluation】
(Select from list)
Document type of this template: "quality record".
■Peer review checklist
Select checklist type from the list.
The "review organizer" will determine whether checklist is to be used.
■Participants
Describe the participants in meeting according to their roles.
All reviewers will be listed.
Refer to "Software Development: Implementation Standard for Review" (RCT-JB5001-002) for role definition.
■Objective of peer review (description of peer review)
Describe the objective or content of peer review.
【Example】 Verify that customer's requests, requirement-related materials created based on investigated requests, and project overview document are adequate and
validated.
Besides, based on the matters which require close attention when receiving the requests, verify the pass/fail condition of the requirement acceptance.
■Meeting
Describe the meeting date, start time, end time and number or participants.
□Meeting date □Start time
Describe meeting date in dd/mm/yyyy format. Describe the start time in hh:mm format.
【Example】 20/10/2016 【Example】 10:00
□End time □Meeting Number of participants
Describe the end time in hh:mm format. Describe the number of persons taking part in the meeting.
【Example】 12:00
□Meeting location
Describe the location the meeting is to be held.
【Example】 Meeting room no. 1
■Review objects
Describe title, file name, version, target scale of the work products indicated to be reviewed in project plan.
Select the unit for target scale from the list. The total scale will be automatically calculated.
If the cells are not enough to describe the objects to be reviewed, contact the Development process improvement department.
■Additional description regarding document issuing
The issuing of the document should be registered as below:
①If peer review checklist (provided by Development process improvement department) is used ②If peer review checklist (created by the project team) is used
・Peer review minutes ・Peer review minutes
－"Minutes" sheet －"Minutes" sheet
－"Peer review checklist" sheet ・Peer review checklist (created by the project team)
List of Issue/Question/Resolution
■Location of issue: object ID
Describe the ID of the object to be reviewed which contains issue.
■Location of issue: location
Describe location information such as page number, item number, row number.
■Detected by
Describe the person who detects the issue.
■Description of issue/question
Describe the content of the issue/question.
If issues are to be resolved based on this minutes without filling data into the management table, describe resolution result and resolution completion date (in dd/mm/yyyy
format) into "Completion date/Deadline" column.
If the content of the issues/questions is large and there are not enough cells to describe, contact the Development process improvement department.
【Example】 Risk
There is a possibility that a new standard is issued and compliance to the standard is required by the customer.
【Example】 Problem
The request provider has informed that the setup of test environment is delayed, then test start date will be delayed but release schedule will still have to be kept.
■Classification
Left column: Select "Issue" or "Question" from the list depending on the content described in "Description of issue/question" column.
①Issue
Issue is the general term for defects, risks, problems, AI, ToDo, etc. detected in peer review.
②Question
Question is the QnA (Question and Answer), the discussed content, etc.
Right column: in case of Issue, select Defect/Risk/Problem/Other from the list depending on the content described in "Description of issue/question" column.
①Defect
Defect refers to the defect in products of each process, detected from the start of Functional design process to the completion of Design qualification process.
For details regarding the criteria and notes for defect determination, refer to "Software Development: Implementation Standard for Defect Management" (RCT-JB5001-
012).
②Risk
Risk is the matter which can affect the project QCD (Quality, Cost, Delivery) but has not yet occurred.
③Problem
Problem is the matter which can affect the project QCD (Quality, Cost, Delivery) but has occurred and requires resolution.
④Other
Matters other than ① ~ ③ such as AI, ToDo.
■Processed by
The person who processes the issue/question.
【Example】 Takahashi SC
■Completion date/Deadline
・Describe the deadline to complete resolving the issues if defects, risks, problems are to be described in another template.
・Describe completion date if the issues are resolved via AI, ToDo of the minutes.
■Description of resolution/Question answering
If the classification is Issue, this "Resolution description" column must be described.
Refer to the below points for the content to describe.
①Defect (in-process defect)
If the defect is transcribed into defect management table, describe "Transcribed into defect management table".
②Problem
If the problem is transcribed into problem management table, describe "Transcribed into problem management table".
③Risk
If the risk is transcribed into risk management table, describe "Transcribed into risk management table".
④Other
Transcription location is other than those above. Determine and describe the management method, taking into consideration the project conditions. If the resolution is
completed using this minutes, describe resolution result.
■Verified by
Name of the person who verifies the resolution.
【Example】 Sato B
■Verification date
Describe the date of verification (dd/mm/yyyy).
【Example】 20/10/2014
Peer review evaluation
■Review initiating condition
Verify if ① ~ ② initiating conditions are met.
Describe if the review initiating condition of the project is other than ① and ②.
■Verification result of review initiating conditions
Describe the result of the verification of whether ① ~ ② initiating conditions are met.
■Review completing conditions
Verify if ① ~ ② completing conditions are met.
Describe if the review completing condition of the project is other than ① and ②.
■Review completing conditions and evaluation
Describe the result of the verification and evaluation of whether ① ~ ② completing conditions are met.
■Review measurements
Describe ther review duration (automatically calculated), number of review participants (automatically calculated) and
review Review man hour(automatically calculated).
Describe the review scale (automatically calculated), number of review issues (automatically calculated), number of defects(automatically calculated).
■Review analysis items and analysis evaluation
Describe analysis evaluation regarding analysis items [review issue density (The actual value is automatically calculated), review speed (The actual value is automatically
calculated)].
In case a desired value exists, perform analysis between actual value and desired value.
※ Review issue density is calculated for both on-desk check and meeting, while review speed is calculated only for meeting.
□Tailoring for analysis items
Select from A or B the list below.
A: Analysis is required since tailoring is not to be implemented
B: Analysis is not required since tailoring is to be implemented
□ Analysis evaluation
【Example】 If the work products to be reviewed are evaluated to contain a reasonable number of issues according to review issue density result,
or the review duration is evaluated as appropriate according to review speed result, both of those will not be considered quality problems
■Review result evaluation according to initiating conditions, completing conditions, and analysis evaluation
The result of peer review operation is evaluated based on results of No.1 ~ No.4.
Select the evaluation result from the list below.
A: Re-implement review since the review operation has not been fully completed within a specified duration.
B :Re-implement review since completing conditions are not met.
C: Re-implement review since the review operation as well as analysis of management indicators have not been appropriately implemented even completing conditions are
met.
D: Review operation has been completed since completing conditions are met, no issue occurs for management indicator analysis result and the review operation has been
appropriately implemented.
E: Review operation has been completed since completing conditions are met (management indicators are "not measured/analyzed).
F: Other
If "Other" is selected, describe the detailed evaluation, as well as the method to verify resolution result in case the review operation will not be implemented
even though issue exists, in the cell under data list cell.
■Explanation of "Tailoring for analysis items" list selection item A and B.
A: Analysis is required since tailoring is not to be implemented
B: Analysis is not required since tailoring is to be implemented
■Explanation of "Review result evaluation" list selection item A, B, C, D, E, and F.
A: Re-implement review since the review operation has not been fully completed within a specified duration.
B :Re-implement review since completing conditions are not met.
C: Re-implement review since the review operation as well as analysis of management indicators have not been appropriately implemented even completing conditions are
met.
D: Review operation has been completed since completing conditions are met, no issue occurs for management indicator analysis result and the review operation has been
appropriately implemented.
E: Review operation has been completed since completing conditions are met (management indicators are "not measured/analyzed).
F: Other

## Pass-around
【RENESAS CONFIDENTIAL】 | [11 empty] | #REF!
Inform to: | [11 empty] | Document number
Date of issue
[5 empty] | Document name: | Peer review minutes | [5 empty] | Company name
Issuing department
Project name:
[14 empty] | Approved by |  |  | Created by
Project number:
Process name:
<Cell background color> Light blue: item name, yellow: data list, pink: automatically configured items, grey: invalid
Peer review checklist |  |  |  | Yes (Attached to this template)
Objective of review (description of review)
Participants |  |  |  | Creator |  | Review organizer
Reviewer
On-desk check |  |  |  | Start date |  | End date |  |  | On-desk check Number of participants |  |  |  | On-desk check Total duration
Review objects ※The work products indicated to be reviewed in "Project plan".
Object ID |  | Name |  |  |  |  | File name | [5 empty] | Version |  | Target scale
① | [17 empty] | (Select from list)
② | [17 empty] | (Select from list)
③ | [17 empty] | (Select from list)
④ | [17 empty] | (Select from list)
⑤ | [17 empty] | (Select from list)
⑥ | [17 empty] | (Select from list)
⑦ | [17 empty] | (Select from list)
⑧ | [17 empty] | (Select from list)
⑨ | [17 empty] | (Select from list)
⑩ | [17 empty] | (Select from list)
Total scale
List of Issue/Question/Resolution
No. | Location of issues |  | Detected by | Description of issue/question |  |  | Classification |  | Processed by | Completion date/Deadline |  | Description of resolution/Question answering |  |  |  |  | Verified by | Verification date
| Object ID | Location
1 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
2 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
3 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
4 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
5 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
6 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
7 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
8 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
9 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
10 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
11 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
12 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
13 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
14 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
15 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
16 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
17 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
18 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
19 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
20 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
21 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
22 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
23 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
24 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
25 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
26 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
27 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
28 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
29 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
30 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
31 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
32 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
33 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
34 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
35 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
36 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
37 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
38 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
39 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
40 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
41 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
42 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
43 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
44 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
45 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
46 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
47 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
48 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
49 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
50 | (Select from list) | [5 empty] | (Select from list) | (Select from list)
Peer review evaluation
No. | Item |  |  |  |  | Description
1 | Review initiating condition |  |  |  |  | 【Review initiating conditions】 The initiating conditions of peer review are as follow: ①"7.3.Preparation of peer review" (Implementation Standard for Review) has completed. ②Required participants as specified in project plan are able to take part in. Describe below if the review initiating condition is other than ① and ②.
【Verification result of review initiating conditions】
2 | Review completing conditions |  |  |  |  | 【Review completing conditions】 The completing conditions of peer review are as follow: ①Desired values of analysis items of peer review, specified in project plan, have been obtained. Or, if desired values of analysis items have not been obtained, agreement with the reviewers regarding the reasons has been reached. ②Peer review minutes indicate that all actions regarding the detected issueshave been completed. If unresolved issues exist, agreement with the reviewers regarding the reasons has been reached. Describe below if the completing condition is other than ① and ②.
【Review completing conditions and evaluation】
3 | Review measurements |  |  |  |  | 【Measured value】
[6 empty] | On-desk check |  |  | Review duration |  |  |  | Number of participants |  |  | Review ｍan hour
Review scale (total)
[6 empty] | Number of review issues | 0 |  | Number of defects |  | 0
4 | Review analysis items and analysis evaluation |  |  |  |  | 【Analysis item】
[11 empty] | Target value |  | Performance value | Tailoring for analysis items
[6 empty] | Review defect density (number of review issues/review scale) | [7 empty] | (Select from list)
【Analysis evaluation】
5 | Review result evaluation according to initiating conditions, completing conditions and analysis evaluation |  |  |  |  | 【Review result evaluation】
(Select from list)
Document type of this template: "quality record".
■Peer review checklist
Select checklist type from the list.
The "review organizer" will determine whether checklist is to be used.
■Participants
Describe the participants in on-desk check, meeting according to their roles.
All reviewers will be listed.
Refer to "Software Development: Implementation Standard for Review" (RCT-JB5001-002) for role definition.
■Objective of peer review (description of peer review)
Describe the objective or content of peer review.
【Example】 Verify that customer's requests, requirement-related materials created based on investigated requests, and project overview document are adequate and
validated.
Besides, based on the matters which require close attention when receiving the requests, verify the pass/fail condition of the requirement acceptance.
■On-desk check
Describe the start date, completion date, number of participants and the duration.
□Start date □End date
Describe the start date as well as end date in dd/mm/yyyy format.
【Example】 20/10/2016 【Example】 30/10/2016
□On-desk check Number of participants □On-desk check Total duration
Number of persons taking part in on-desk check. Describe the total on-desk check duration in decimal value (unit: hr).
【Example】 2.5 ※ 2 hours 30 minutes
■Review objects
Describe title, file name, version, target review scope of the work products indicated to be reviewed in project plan.
Select the unit for target review scope from the list. The grand total will be automatically calculated.
If the cells are not enough to describe the products to be reviewed, contact the Process improvement department.
■Additional description regarding document issuing
The issuing of the document should be registered as below:
①If peer review checklist (provided by Development process improvement department) is used ②If peer review checklist (created by the project team) is used
・Peer review minutes ・Peer review minutes
－"Minutes" sheet －"Minutes" sheet
－"Peer review checklist" sheet ・Peer review checklist (created by the project team)
List of Issue/Question/Resolution
■Location of issue: object ID
Describe the ID of the object to be reviewed which contains issue.
■Location of issue: location
Describe location information such as page number, item number, row number.
■Detected by
Describe the person who detects the issue.
■Description of issue/question
Describe the content of the issue/question.
If issues are to be resolved based on this minutes without filling data into the management table, describe resolution result and resolution completion date (in dd/mm/yyyy
format) into "Completion date/Deadline" column.
If the content of the issues/questions is large and there are not enough cells to describe, contact the Development process improvement department.
【Example】 Risk
There is a possibility that a new standard is issued and compliance to the standard is required by the customer.
【Example】 Problem
The request provider has informed that the setup of test environment is delayed, then test start date will be delayed but release schedule will still have to be kept.
■Classification
Left column: Select "Issue" or "Question" from the list depending on the content described in "Description of issue/question" column.
①Issue
Issue is the general term for defects, risks, problems, AI, ToDo, etc. detected in peer review.
②Question
Question is the QnA (Question and Answer), the discussed content, etc.
Right column: in case of Issue, select Defect/Risk/Problem/Other from the list depending on the content described in "Description of issue/question" column.
①Defect
Defect refers to the defect in products of each process, detected from the start of Functional design process to the completion of Design qualification process.
For details regarding the criteria and notes for defect determination, refer to "Software Development: Implementation Standard for Defect Management" (RCT-JB5001-
012).
②Risk
Risk is the matter which can affect the project QCD (Quality, Cost, Delivery) but has not yet occurred.
③Problem
Problem is the matter which can affect the project QCD (Quality, Cost, Delivery) but has occurred and requires resolution.
④Other
Matters other than ① ~ ③ such as AI, ToDo.
■Processed by
The person who processes the issue/question.
【Example】 Takahashi SC
■Completion date/Deadline
・Describe the deadline to complete resolving the issues if defects, risks, problems are to be described in another template.
・Describe completion date if the issues are resolved via AI, ToDo of the minutes.
■Description of resolution/Question answering
If the classification is Issue, this "Resolution description" column must be described.
Refer to the below points for the content to describe.
①Defect (in-process defect)
If the defect is transcribed into defect management table, describe "Transcribed into defect management table".
②Problem
If the problem is transcribed into problem management table, describe "Transcribed into problem management table".
③Risk
If the risk is transcribed into risk management table, describe "Transcribed into risk management table".
④Other
Transcription location is other than those above. Determine and describe the management method, taking into consideration the project conditions. If the resolution is
completed using this minutes, describe resolution result.
■Verified by
Name of the person who verifies the resolution.
【Example】 Sato B
■Verification date
Describe the date of verification (dd/mm/yyyy).
【Example】 20/10/2014
Peer review evaluation
■Review initiating condition
Verify if ① ~ ② initiating conditions are met.
Describe if the review initiating condition of the project is other than ① and ②.
■Verification result of review initiating conditions
Describe the result of the verification of whether ① ~ ② initiating conditions are met.
【Example】 Initiating conditions are fully met.
■Review completing conditions
Verify if ① ~ ② completing conditions are met.
Describe if the review completing condition of the project is other than ① and ②.
■Review completing conditions and evaluation
Describe the result of the verification and evaluation of whether ① ~ ② completing conditions are met.
【Example】 Review completing conditions are fully met, review operation can be completed.
■Review measurements
Describe ther review duration (automatically calculated), number of review participants (automatically calculated) and
review Review man hour(automatically calculated).
Describe the review scale (automatically calculated), number of review issues (automatically calculated), number of defects(automatically calculated).
■Review analysis items and analysis evaluation
Describe analysis evaluation regarding analysis items [review issue density (The actual value is automatically calculated), review speed (The actual value is automatically
calculated)].
In case a desired value exists, perform analysis between actual value and desired value.
※ Review finding density is calculated for both on-desk check and meeting, while review speed is calculated only for meeting.
□Tailoring for analysis items
Select from A or B the list below.
A: Analysis is required since tailoring is not to be implemented
B: Analysis is not required since tailoring is to be implemented
□ Analysis evaluation
【Example】 If the work products to be reviewed are evaluated to contain a reasonable number of issues according to review issue density result,
it can be considered that no quality issue exists.
■Review result evaluation according to initiating conditions, completing conditions, and analysis evaluation
The result of peer review operation is evaluated based on results of No.1 ~ No.4.
Select the evaluation result from the list below.
A: Re-implement review since the review operation has not been fully completed within a specified duration.
B :Re-implement review since completing conditions are not met.
C: Re-implement review since the review operation as well as analysis of management indicators have not been appropriately implemented even completing conditions are
met.
D: Review operation has been completed since completing conditions are met, no issue occurs for management indicator analysis result and the review operation has been
appropriately implemented.
E: Review operation has been completed since completing conditions are met (management indicators are "not measured/analyzed).
F: Other
If "Other" is selected, describe the detailed evaluation, as well as the method to verify resolution result in case the review operation will not be implemented
even though issue exists, in the cell under data list cell.
■Explanation of "Tailoring for analysis items" list selection item A and B.
A: Analysis is required since tailoring is not to be implemented
B: Analysis is not required since tailoring is to be implemented
■Explanation of "Review result evaluation" list selection item A, B, C, D, E, and F.
A: Re-implement review since the review operation has not been fully completed within a specified duration.
B :Re-implement review since completing conditions are not met.
C: Re-implement review since the review operation as well as analysis of management indicators have not been appropriately implemented even completing conditions are
met.
D: Review operation has been completed since completing conditions are met, no issue occurs for management indicator analysis result and the review operation has been
appropriately implemented.
E: Review operation has been completed since completing conditions are met (management indicators are "not measured/analyzed).
F: Other

## Peer review checklist
Software development for software product or system product
Peer review checklist: request table, product requirement table
ID | Item | Verification | Additional description
1 | Are the following points considered when investigating the requests? ・Needs: requests regarding the products. ・Expectations: requests to be implemented for the products. ・Constraints: cost, schedule, performance, functionality, maintainability, introduction of third party right. ・Interface: requests related to the internal/external interface of a software product. ・Required legal requirements, as well as typical standard requirements defined by industry groups, depending on location of use of a software product, environment, and limiting conditions. ・Software licensing: things to be ensured, scope and duration of the provided license. | (Select from list)
2 | Is the request acceptance evaluation implemented based on the below criteria? ・Clarity, ease of understanding (consistent content explanation). ・No contradiction between multiple requests. ・Design can be completed within the defined period of time. ・Unfeasible design functions are not included. ・Testing can be implemented. ・The matters to be considered for request investigation. | (Select from list)
3 | Are the following points considered when converting to product requirements? ・Specifications of interface between functions and software units. ・Non-conformance between software product functions and product requirements. ・Requested quality of the work products. ・Work product dependency. | (Select from list)
4 | Do the product requirements meet the Needs, Expectations & Constraints of the request provider and the stakeholders? | (Select from list)
5 | Are the product requirements adequately defined for the assumed operations (no excess or deficiency)? | (Select from list)
Peer review checklist: project plan
ID | Item | Verification | Additional description
1 | Is the content described regarding project conditions, constraints, requests and usable resources feasible? | (Select from list)
2 | If no question or deficiency issue exists, is the linking to related projects planned? | (Select from list)
3 | Is the tailoring result described into project plan? | (Select from list)
4 | Is the document which describe estimation-related information such as estimation method, the rationale for product scale calculation, the rationale for effort calculation available? | (Select from list)
5 | If training is required to improve specific skills, are you planning a training ? | (Select from list)
6 | Are the stakeholders of the project specifically defined? | (Select from list)
Peer review checklist: functional design specification
ID | Item | Verification | Additional description
1 | Is the functional design specification updated in case of any specification is changed related to the function? | (Select from list)
2 | Is the traceability verified? (to eliminate omission issue regarding the requirements)
| ・Are traceability maps, traceability matrices, tools, etc. created as a means of securing traceability? | (Select from list)
3 | Is it confirmed that there is no ambiguous description?
| · Does the operation when the parameter is omitted are clearly described? | (Select from list)
| ・Is the upper/lower threshold of the variable described? | (Select from list)
| · Is the error occurrence condition of software processing and the processing after error occurrence clearly described? | (Select from list)
4 | Is sentence easy to understand? (using point of view below)
| · Is the specification / condition of errors described in a uniform manner? | (Select from list)
| · Is the word to be used unified? (no different expressions exist regarding the same thing) | (Select from list)
| ・Is the glossary for the terminologies used in documents of the project created? (the glossary is for unifying the use of terminologies and is not mandatory) | (Select from list)
5 | When describing the same content in multiple places, are there no contradictions in the description contents? (consistency inside a document and among documents) | (Select from list)
6 | Are the all items which should not be disclosed to users described "Not Disclose"? | (Select from list)
7 | Is sentence easy to understand? (using point of view below)
| ・Is sentence simple and short ? | (Select from list)
| · Is the qualification of the modifier clear? | (Select from list)
8 | Is the consistency check with the other specifications/design documents (hardware, tool) performed by using point of view below?
| ・Are the hardware-related items in functional design specification described by referring hardware specifications/design documents? | (Select from list)
| ・Is it verified that if other specifications/design documents are upgraded? | (Select from list)
| ・In case of other specifications / design documents are updated, are the differences reflected in the functional design specification? | (Select from list)
| ・Is the terminology unification performed using terminologies of the reference document? | (Select from list)
9 | Are the related hardware/tools (such as OS/compilers) clearly described? | (Select from list)
10 | Is the IF with the tool described? - The debug environment which utilizes compiler/linker (such as sections), tracer, code generation, self-programming devices, monitor. | (Select from list)
11 | Are the device-dependent specifications clearly described? | (Select from list)
12 | Are the resources of the device to be used by software clearly described? | (Select from list)
13 | In case of requirements are not clearly defined or are not provided yet to create functional design specification, Are these managed as risk, problem, or ToDo? | (Select from list)
14 | Is the module name or function name according to the naming convention? | (Select from list)
15 | Is the interface designed according to interface specifications which include specification components required for design such as timing, protocol, rule, data format, etc.? | (Select from list)
Peer review checklist: Detailed Design specification
ID | Item | Verification | Additional description
1 | Is the detailed design specification updated in case of any specification is changed related to the function? | (Select from list)
2 | Is the traceability verified? (to eliminate omission issue regarding the requirements)
| ・Are traceability maps, traceability matrices, tools, etc. created as a means of securing traceability? | (Select from list)
3 | Is it confirmed that there is no ambiguous description?
| · Does the operation when the parameter is omitted are clearly described? | (Select from list)
| ・Is the upper/lower threshold of the variable described? | (Select from list)
| · Is the error occurrence condition of software processing and the processing after error occurrence clearly described? | (Select from list)
4 | Is sentence easy to understand? (using point of view below)
| · Is the specification / condition of errors described in a uniform manner? | (Select from list)
| · Is the word to be used unified? (no different expressions exist regarding the same thing) | (Select from list)
| ・Is the glossary for the terminologies used in documents of the project created? (the glossary is for unifying the use of terminologies and is not mandatory) | (Select from list)
5 | When describing the same content in multiple places, are there no contradictions in the description contents? (consistency inside a document and among documents) | (Select from list)
6 | Are the all items which should not be disclosed to users described "Not Disclose"? | (Select from list)
7 | Is sentence easy to understand? (using point of view below)
| ・Is sentence simple and short ? | (Select from list)
| · Is the qualification of the modifier clear? | (Select from list)
8 | Is the consistency check with the other specifications/design documents (hardware, tool) performed by using point of view below?
| ・Are the hardware-related items in functional design specification described by referring hardware specifications/design documents? | (Select from list)
| ・Is it verified that if other specifications/design documents are upgraded? | (Select from list)
| ・In case of other specifications / design documents are updated, are the differences reflected in the functional design specification? | (Select from list)
| ・Is the terminology unification performed using terminologies of the reference document? | (Select from list)
9 | Are the related hardware/tools (such as OS/compilers) clearly described? | (Select from list)
10 | Is the IF with the tool described? - The debug environment which utilizes compiler/linker (such as sections), tracer, code generation, self-programming devices, monitor. | (Select from list)
11 | Are the device-dependent specifications clearly described? | (Select from list)
12 | Are the resources of the device to be used by software clearly described? | (Select from list)
13 | In case of requirements are not clearly defined or are not provided yet to create functional design specification, Are these managed as risk, problem, or ToDo? | (Select from list)
14 | Is the arrangement condition of the function / table (including members) considering alignment to memory? | (Select from list)
15 | Is the variable / function being verified from the following viewpoints?
| Is the necessity of members being verified? | (Select from list)
| ・Is the member variable/method type appropriate? Have not set unnecessary public modifiers when declaring member variables? | (Select from list)
| ・Is the timing and initial value to initialize a variable clearly described? | (Select from list)
| ・Is the variable name being verified to be suitable for type / size? | (Select from list)
16 | Is the module name or function name according to the naming convention? | (Select from list)
17 | Is the function parameters consistent from the following viewpoint (order, type, etc.)?
| ・Are both types int and uint used for a similar value? | (Select from list)
| ・Is the order of the arguments not different for a similar input parameter? | (Select from list)
18 | Is the termination condition clearly described for each module ? | (Select from list)
19 | Is the relationship of reference for modules clearly described? | (Select from list)
20 | Is the method to access data clearly described? | (Select from list)
21 | If it's required to select the most appropriate method from multiple design methods, are the selected process, evaluation result and the basis of this evaluation described into Detailed Design specification? | (Select from list)
Peer review checklist: source code
ID | Item | Verification | Additional description
1 | Is the traceability verified? (to eliminate omission issue regarding the requirements)
| ・Are traceability maps, traceability matrices, tools, etc. created as a means of securing traceability? | (Select from list)
2 | Is the analysis of the impact to the source code by the function change being sufficiently implemented? | (Select from list)
3 | Is the analysis result of the impact to source code presented as peer review supplementary material? | (Select from list)
4 | Show change analysis result as supplementary review materials (in appropriate format depending on property of the changes). | (Select from list)
5 | Is the result of executing the compiler / link being verified that there is no error / warning? | (Select from list)
6 | Was the static analysis performed using the tool specified in the project plan? | (Select from list)
7 | Is the source code created to comply according to coding rules specified in the project? | (Select from list)
8 | Does it confirmed that there is no unnecessary "ifdef" in the source code? e.g.) "ifdef" used for debugging, and forget to remove it. | (Select from list)
9 | Are the error messages, error code number/content consistent with the specifications? | (Select from list)
10 | Does it confirmed that there is no immediate value in the source code ? | (Select from list)
11 | Are all the variables initialized? | (Select from list)
12 | Is the upper / lower threshold of the variable verified?
| ・Are the variables/arrays not overflowed (underflowed) in incrementing/decrementing components? | (Select from list)
13 | Is the loop process being verified from the following viewpoints?
| ・Are the starting / completing conditions matched to descriptions in detailed design specification ? | (Select from list)
| ・Are the variables / arrays not overflowed (underflowed)? | (Select from list)
14 | Are the comments written according to the coding rules? | (Select from list)
15 | Is branch conditions confirmed by viewpoint below ?
| ・Are ">" and "<" correctly used? Is "=" not necessary? | (Select from list)
16 | Is the coding of two-byte characters consistently performed? (Basically UTF-8 should be used. Other type can be used in case of definition in the project-specific rules.) | (Select from list)
17 | Is the update of product version implemented?
| ・The ID for binary identification such as internal version number, not only the major/minor version defined in project plan. | (Select from list)
Peer review checklist: test specifications
ID | Item | Verification | Additional description
1 | Is the test specification updated in case of any specification is changed related to the test? | (Select from list)
2 | Is the test item addition or the content of test item changing performed in case of specification change which is related to processing speed ? | (Select from list)
3 | Is the traceability verified? (to eliminate omission issue regarding the requirements)
| ・Are traceability maps, traceability matrices, tools, etc. created as a means of securing traceability? | (Select from list)
4 | Have you prepared test specifications from the following viewpoint so that you can understand test items uniquely?
| ・Is a test condition clearly described? (task, interrupt, service name, service issuing context, priority, etc.) | (Select from list)
| ・Is the expected value written in easy-to-understand sentences? Also, if it is possible to describe by numerical value, is it stated numerically? | (Select from list)
| · Is the test specification described so that a single interpretation is possible? | (Select from list)
5 | Is the wording unified? (no different expressions exist regarding the same thing)
| ・Is the glossary for the terminologies used in documents of the project created? (the glossary is for unifying the use of terminologies and is not mandatory) | (Select from list)
6 | When describing the same content in multiple places, are there no contradictions in the description contents? (consistency inside a document and among documents)
| · When describing the same content in multiple places, Have you clearly stated the link to the relevant content for each of the items ? | (Select from list)
7 | Is sentence easy to understand? (using point of view below)
| ・Is sentence simple and short ? | (Select from list)
| · Is the qualification of the modifier clear? | (Select from list)
8 | Are the device-dependent specifications clearly described? | (Select from list)
9 | In case of requirements or specifications are not clearly defined or are not provided yet to create test specification, Are these managed as risk, problem, or ToDo? | (Select from list)
10 | Do you confirm the unit test point of view below ?
| ・Is there any impossible combination? | (Select from list)
| ·Do you describe untested combination and untested reason in test specification ? | (Select from list)
11 | Is the upper / lower limit value in each test item consistent with the description in detailed design specification ? | (Select from list)
12 | Are all execution environments necessary for testing written? | (Select from list)
13 | Is the product integration (integration environment, integration tool, integration process and integration completion process) described? | (Select from list)
Peer review checklist: test environment
ID | Item | Verification | Additional description
1 | In order to avoid misusing, is the version of test object checked ? | (Select from list)
2 | Did you check the version of the test environment including development tools ? | (Select from list)
3 | If communication with other systems is necessary in system test, are related systems prepared ? | (Select from list)
4 | Are all the documents necessary for testing prepared ? | (Select from list)
Peer review checklist: test result
ID | Item | Verification | Additional description
1 | Is the test performed on all environments specified in test specifications and logs are obtained? | (Select from list)
2 | Does the test result contain any defects? (are all test items PASS?) | (Select from list)
3 | Are all test items specified in test specifications tested? (are the test items adequately (no excess or deficiency) tested?) | (Select from list)
4 | (Performance evaluation) Is the performance measurement result correctly measured, and are the values validated? | (Select from list)
5 | (Performance evaluation) Does the performance measurement result achieve the desired values specified in project plan? | (Select from list)
6 | Is the all environment for the all test described in test report? | (Select from list)
7 | Are the limitations described into the test report, if any? | (Select from list)
8 | Are all logs available for reference from the test report ? e.g.) File names and the log registration location are clearly described. | (Select from list)
■Additional description ①This peer review checklist is provided by the Process improvement department.
②In case the peer review checklist created
by the project is to be used, do not use this checklist.
③This checklist is to be used in software development project for software products or system products.
④For the target processes (Requirement development process ~ System test process), check the products of each process.
⑤This peer review checklist is used to check the products of relevant processes only.
For the unused check items of other processes, grey out and specifically describe that the items are unused.
⑥This peer review checklist must be filled before peer review is implemented.
Verify the filled content in peer review.
Verify each checklist item, describe the evaluation or additional description.
■Verification
Select "○", "×", or "N/A. ・○: check result "OK".
・×: check result "NG".
・N/A: verification not required.
■Additional description
Describe the reason to judge "NG", the reason no need to correct it and etc.

## Template Revision history (hidden)
[RENESAS CONFIDEINTIAL]
[Template name: peer review minutes, Version 20170331]
【Revision history】The template revision history describes the change contents of the template itself.
Revision | Description of change | Approver | Author
20161001 | Initial issue | Etani SS | Etani SS
20161101 | Bug fixes | Etani SS | Etani SS
20161202 |  | Etani SS | Masukawa SC
20170331 | Changed items in the peer review checklist. | Etani SS | Kurokawa SC